## kyrell's project board - ai-age
Kyrell's Project Board - AI-agentic SOC triage engine
Week 1- Project Foundation & Planning
Name | Subitems | Person | Status | Date | Checkbox | Item ID (auto generated)
Project Setup & Development Environment |  | Kyrell Green | Done | 2026-08-17 | v | 12726202658
Design the Alert Schema |  | Kyrell Green | Done |  |  | 12726300556
Learn FastAPI Fundamentals |  | Kyrell Green | Done |  |  | 12726350604
Build the Identity API Skeleton |  | Kyrell Green | Done |  |  | 12726389663
TEST/Debug |  |  | Working on it |  |  | 12737974625
Status Update |  |  | Done | 2026-08-20 | v | 12856971058
|  |  |  | 2026-08-17 to 2026-08-20 | 2/6
Week 2- Building the identity source
Name | Subitems | Person | Status | Date | Checkbox | Item ID (auto generated)
Learn Pydantic Models |  | Kyrell Green | Done | 2026-08-24 |  | 12726484445
Generate Synthetic Identity Data |  | Kyrell Green | Done | 2026-08-25 |  | 12726437133
Connect FastAPI to PostgreSQL |  | Kyrell Green | N/A | 2026-08-26 |  | 12726460552
Attack Scenario Generator |  | Kyrell Green | Done | 2026-08-27 |  | 12726485623
TEST/Debug |  |  | Working on it |  |  | 12737960971
|  |  |  | 2026-08-24 to 2026-08-27 | 0/5
Week 3- SIEM mock service -> "Wazuh Integration"
Name | Subitems | Person | Status | Date | Checkbox | Item ID (auto generated)
Design the SIEM Event Schema |  | Kyrell Green | Done | 2026-08-31 |  | 12715429015
Build the SIEM FastAPI Service |  | Kyrell Green | Done | 2026-09-01 |  | 12715428090
Generate SIEM Attack Events |  | Kyrell Green | Done | 2026-09-02 |  | 12715481534
Integration Testing & Project Review |  | Kyrell Green | Done | 2026-09-03 |  | 12715398467
TEST/Debug |  | Kyrell Green |  |  |  | 12737980224
|  |  |  | 2026-08-31 to 2026-09-03 | 0/5
Week 4- Build the EDR Mock Service
Name | Subitems | Person | Status | Date | Checkbox | Item ID (auto generated)
Design the EDR Data Model |  | Kyrell Green | Done | 2026-09-07 |  | 12715482241
Generate Synthetic Endpoint Telemetry |  | Kyrell Green | Done | 2026-09-08 |  | 12715484072
Build the EDR FastAPI Service |  | Kyrell Green | Done | 2026-09-09 |  | 12715483928
End-to-End API Integration |  | Kyrell Green | Done | 2026-09-10 |  | 12715481949
Weekly Goal | [5 empty] | 12726641813
Monthly Presentation |  |  |  | 2026-09-10 | v | 13019911458
|  |  |  | 2026-09-07 to 2026-09-10 | 1/6
WEEK 5- Learn LangGraph & Build the Supervisor
Name | Subitems | Person | Status | Date | Checkbox | Item ID (auto generated)
Learn LangGraph Fundamentals |  | Kyrell Green | Done | 2026-09-14 |  | 12726676250
Create the Investigation State |  | Kyrell Green | Done | 2026-09-15 |  | 12726699225
Build the Supervisor Node |  | Kyrell Green | Done | 2026-09-16 |  | 12726690477
Build the First Tool |  | Kyrell Green | Done | 2026-09-17 |  | 12726726941
Weekly Goal |  | Kyrell Green |  |  |  | 12726794813
Status update |  |  |  |  | v | 13076056100
|  |  |  | 2026-09-14 to 2026-09-17 | 1/6
WEEK 6- Connect the Investigation Engine
Name | Subitems | Person | Status | Date | Checkbox | Item ID (auto generated)
Connect the SIEM Tool |  | Kyrell Green | Done | 2026-09-21 |  | 12726786427
Connect the EDR Tool |  | Kyrell Green | Done | 2026-09-22 |  | 12726761012
Build the Investigation Timeline |  | Kyrell Green | Done | 2026-09-23 |  | 12726834681
Weekly Goal |  | Kyrell Green |  |  |  | 12726841316
|  |  |  | 2026-09-21 to 2026-09-23 | 0/4
WEEK 7- Correlation & MITRE ATT&CK Mapping
Name | Subitems | Person | Status | Date | Checkbox | Item ID (auto generated)
Complete the First Automated Investigation |  | Kyrell Green | Done | 2026-09-28 |  | 12726816232
Design the Investigation Correlation Engine |  | Kyrell Green | Done | 2026-09-29 |  | 12727557582
Build the Correlation Engine |  | Kyrell Green | Done | 2026-09-30 |  | 12727525999
Implement MITRE ATT&CK Mapping |  | Kyrell Green | Done | 2026-10-01 |  | 12727577701
Validate All Attack Scenarios |  | Kyrell Green | Done | 2026-10-02 |  | 12727597585
Weekly Summary |  | Kyrell Green |  |  |  | 12727548441
|  |  |  | 2026-09-28 to 2026-10-02 | 0/6
WEEK 8- A.I. report Generation
Name | Subitems | Person | Status | Date | Checkbox | Item ID (auto generated)
Design the Investigation Report |  | Kyrell Green | Done | 2026-10-05 |  | 12727631792
Generate AI Investigation Summaries |  | Kyrell Green |  | 2026-10-06 |  | 12727694453
Implement Investigation Logging |  | Kyrell Green |  | 2026-10-07 |  | 12727666620
Complete the First End-to-End Investigation |  | Kyrell Green |  | 2026-10-08 |  | 12727688142
Weekly Goal |  | Kyrell Green |  |  |  | 12727636140
|  |  |  | 2026-10-05 to 2026-10-08 | 0/5
WEEK 9- Human-in-the-Loop Workflow
Name | Subitems | Person | Status | Date | Checkbox | Item ID (auto generated)
Design the Approval Workflow |  | Kyrell Green |  | 2026-10-12 |  | 12727706291
Implement the Approval Gate |  | Kyrell Green |  | 2026-10-13 |  | 12727753589
Build the Analyst Console (CLI Version) |  | Kyrell Green |  | 2026-10-14 |  | 12727762641
Adversarial Testing |  | Kyrell Green |  | 2026-10-15 |  | 12727768361
Weekly Goal |  | Kyrell Green |  |  |  | 12727747896
|  |  |  | 2026-10-12 to 2026-10-15 | 0/5
WEEK 10- Build the SOC Dashboard
Name | Subitems | Person | Status | Date | Checkbox | Item ID (auto generated)
Learn Streamlit Fundamentals |  | Kyrell Green |  | 2026-10-19 |  | 12727820750
Build the Alert Queue |  | Kyrell Green |  | 2026-10-20 |  | 12727818972
Display Investigation Results |  | Kyrell Green |  | 2026-10-21 |  | 12727878257
Implement Approval Buttons |  | Kyrell Green |  | 2026-10-22 |  | 12727914405
Weekly Goal |  | Kyrell Green |  |  |  | 12727892990
|  |  |  | 2026-10-19 to 2026-10-22 | 0/5
Testing & Evaluation
Name | Subitems | Person | Status | Date | Checkbox | Item ID (auto generated)
Generate the Test Dataset |  | Kyrell Green |  | 2026-10-26 |  | 12727960162
Run Full System Evaluation |  | Kyrell Green |  | 2026-10-27 |  | 12727943787
Measure Performance |  | Kyrell Green |  | 2026-10-28 |  | 12727971285
Improve the Investigation Engine |  | Kyrell Green |  | 2026-10-29 |  | 12727989038
Weekly Goal |  | Kyrell Green |  |  |  | 12727911635
|  |  |  | 2026-10-26 to 2026-10-29 | 0/5
Documentation, Portfolio & Final Touches
Name | Subitems | Person | Status | Date | Checkbox | Item ID (auto generated)
Write the Technical Documentation |  | Kyrell Green |  | 2026-11-02 |  | 12727982226
Record the Project Demo |  | Kyrell Green |  | 2026-11-03 |  | 12728018274
Write Your Portfolio Case Study |  | Kyrell Green |  | 2026-11-04 |  | 12728091315
Final QA & Project Release |  | Kyrell Green |  | 2026-11-05 |  | 12728038632
Weekly Goal |  | Kyrell Green |  |  |  | 12728068589
|  |  |  | 2026-11-02 to 2026-11-05 | 0/5

## Rubric Summary
Rubric coverage summary
All counts are formulas over 'Rubric Checklist' and 'Board Additions'; change a Status there and this sheet updates.
Environment note: the IR rubric names Parrot OS + VirtualBox + macOS; your lab is Kali + UTM + Dockerized Wazuh on a Mac. Confirm the substitution with your instructor (board subitem on Oct 12).
Partial credit weight | 50% | Assumption: a 'Partial' row counts as half done in % complete (my choice; edit to taste).
Rubric | Crit. | Criterion | Requirements | Done | Partial | Not started | % complete | Board subitems linked
Security Monitoring | M1 | Monitoring Environment Setup | 5 | 2 | 3 | 0 | 70% | 3
Security Monitoring | M2 | Security Event Analysis | 5 | 4 | 1 | 0 | 90% | 0
Security Monitoring | M3 | Monitoring Implementation | 5 | 2 | 1 | 2 | 50% | 2
Security Monitoring | M4 | Security Reporting | 5 | 0 | 5 | 0 | 50% | 4
Incident Response | I1 | IR Environment Setup | 6 | 1 | 4 | 1 | 50% | 4
Incident Response | I2 | Incident Detection and Analysis | 4 | 1 | 3 | 0 | 62.5% | 3
Incident Response | I3 | Incident Response and Containment | 3 | 0 | 3 | 0 | 50% | 3
Incident Response | I4 | Digital Evidence Management | 5 | 0 | 2 | 3 | 20% | 3
Incident Response | I5 | IR Documentation and Reporting | 4 | 2 | 2 | 0 | 75% | 2
Incident Response | I6 | Post-Incident Procedures | 4 | 2 | 1 | 1 | 62.5% | 1
Security Monitoring |  |  | 20 | 8 | 10 | 2 | 65% | 9
Incident Response |  |  | 26 | 6 | 15 | 5 | 51.92% | 16
Overall |  |  | 46 | 14 | 25 | 7 | 57.61% | 25

## Rubric Checklist
Rubric checklist: Security Monitoring + Incident Response
Edit only the Status column (dropdown) and add links in 'Existing evidence' as you capture them. Status reflects the repo as of Oct 12, 2026 plus your Oct 5-8 notes; re-check anything marked Done before submitting.
Target date = earliest linked subitem on 'Board Additions' (assumption: set by me from the board's week windows).
ID | Rubric | Crit. | Criterion | Requirement | Board tie-in | Existing evidence | Gap / next action | Status | Target date
M1.1 | Security Monitoring | M1 | Monitoring Environment Setup | Wazuh (or similar) installed and configured, with evidence of network configuration | Week 3 - Wazuh Integration | Wazuh 4.14.7 Docker stack; ARCHITECTURE.md; SIEM_Implementation.md; Network_Topology report (10.11.0.0/22) | Add a 'docker compose ps' screenshot and one dashboard screenshot | Done
M1.2 | Security Monitoring | M1 | Monitoring Environment Setup | Log collection from 2+ source types (Windows and Linux) with verified connectivity | Week 3 / AGENT_DEPLOYMENT_STATUS | Agent 002 Kali (Linux) and agent 007 DESKTOP-VCKJCPV (Windows, enrolled 2026-09-23); Ping.png; test_wazuh_connection.py | Screenshot of Agents page showing both Active | Done
M1.3 | Security Monitoring | M1 | Monitoring Environment Setup | Alert rules for 3+ scenarios (authentication, file access, network activity) | Week 3; Week 9 adds | Auth: stock 5763/40112 plus custom 100002/100003. Windows: custom 100010/100011. Network: custom 100020/100021 (Suricata). File access: stock FIM rule 550 | Show rules in local_rules.xml + logtest proof; confirm Suricata alerts reach Wazuh; fix ID 100010 meaning in older docs | Partial | 2026-10-14
M1.4 | Security Monitoring | M1 | Monitoring Environment Setup | Basic monitoring workflow showing alert routing and notification configuration | Week 9 - Approval Gate | SOC_Operations.md workflow (alert to TheHive to analyst). Live ossec.conf had email_notification = no and no Wazuh-to-TheHive connector as of Oct 5 | Configure one real path (email or TheHive integration) and capture a test alert | Partial | 2026-10-13
M1.5 | Security Monitoring | M1 | Monitoring Environment Setup | Screenshots: dashboard, configuration files, log collection, rule triggering | Week 9 | 5 screenshots in ai-agentic-soc/screenshots (agent deployment, agents list, ping, test server, Aug 19 dashboard) | Missing: ossec.conf, local_rules.xml, a rule-trigger (5763/40112) view | Partial | 2026-10-14
M2.1 | Security Monitoring | M2 | Security Event Analysis | Analysis of 3+ log types with clear interpretation methodology | Week 7 - Correlation | Threat_Detection_Principles.md: sshd auth, FIM, Windows event channel, SCA, vulnerability detector | None | Done
M2.2 | Security Monitoring | M2 | Security Event Analysis | Correlation between 2+ log sources showing related events | Week 7 - Correlation Engine | Auth log (passwd labtester, rule 5402) + FIM /etc/shadow change (rule 550); evidence gatherer joins Wazuh + identity + EDR | Label the two sources explicitly as a correlation exercise. Do not use the Suricata replay (synthetic 2002 timestamps) as a correlation source | Done
M2.3 | Security Monitoring | M2 | Security Event Analysis | Complete incident detection scenario: timeline, correlation, conclusions | Week 8 - First End-to-End Investigation | SOC-CASE-2026-0142 (rule 40112 level 12, 71 ms session, no post-access activity) | None | Done
M2.4 | Security Monitoring | M2 | Security Event Analysis | Alert triage process: severity assessment, false-positive identification, escalation criteria | Week 9 - Approval Workflow | Incident_Response_Template A.9 severity matrix; Methodology escalation triggers D1-D7; benign examples (rootcheck 510, DCOM 61110) | Put the false-positive examples in a table inside the repo docs | Partial
M2.5 | Security Monitoring | M2 | Security Event Analysis | Annotated log excerpts, interpretation of findings, investigation methodology | Week 8 - Logging | Methodology sec. 6 and 8 (verbatim full_log lines, queries to re-derive) | None | Done
M3.1 | Security Monitoring | M3 | Monitoring Implementation | Monitoring architecture diagram with components and data flows | Week 3 | Mermaid diagrams in SIEM_Implementation sec. 1.2 and Monitor_and_Respond sec. 1.1 | Export one combined image including TheHive, Suricata and the triage engine | Done
M3.2 | Security Monitoring | M3 | Monitoring Implementation | 3+ data sources integrated with evidence of successful collection | Week 3-4 | Linux auth/journald, Windows event channel, FIM, SCA, vulnerability detector; indexer queries in Methodology sec. 8 | Screenshot of each source in Discover | Done
M3.3 | Security Monitoring | M3 | Monitoring Implementation | Performance baselines for normal operations with defined alert thresholds | Week 10 | Wazuh rule 11 fired on 2026-10-01 ('average 561, reached 1812') - an existing baseline signal | Build baseline table from indexer (alerts/day per agent, failed logins per source) and state thresholds | Not started | 2026-10-20
M3.4 | Security Monitoring | M3 | Monitoring Implementation | Health monitoring: collection status, processing performance, storage utilization | Week 10 | IndexerClient.ping(); /agents status; /manager/status; known Docker VM RAM limit (7.7 GiB) | Write health_check.py and document the procedure | Not started | 2026-10-20
M3.5 | Security Monitoring | M3 | Monitoring Implementation | Implementation docs: config files, integration steps, baselines, health check procedures | Week 11 - Technical Documentation | README.md; SIEM_Implementation.md; ARCHITECTURE.md | Baselines and health procedures missing (see M3.3, M3.4) | Partial
M4.1 | Security Monitoring | M4 | Security Reporting | Standardized alert documentation template used for 3+ alert types | Testing and Evaluation | Incident_Response_Template.md (Sections A-J); 1 completed instance (0142) | Complete 2 more types (e.g. vulnerability CVE, SCA score, Windows account change) | Partial | 2026-10-26
M4.2 | Security Monitoring | M4 | Security Reporting | Security metrics: operational, coverage, effectiveness, with measurement methods | Testing - Measure Performance | 0142: declared about 2 min, D3 under 1 min, contained T+20. Board task already plans accuracy / FP / FN | Consolidate into one metrics table with a method per metric | Partial | 2026-10-28
M4.3 | Security Monitoring | M4 | Security Reporting | Security summary report: alert trends, significant findings, recommendations | Documentation week | Findings I.1-I.9 in the IR report; weekly status updates | Add alert-trend section from indexer counts | Partial | 2026-11-04
M4.4 | Security Monitoring | M4 | Security Reporting | At least one dashboard showing real-time security status with visualizations | Week 10 - SOC Dashboard | Wazuh dashboard is live; Streamlit alert queue planned Oct 19-22 | Decide which dashboard you submit; add health panel | Partial | 2026-10-21
M4.5 | Security Monitoring | M4 | Security Reporting | Professional standards: organization, appropriate detail, actionable information | All documentation | Consistent rubric-coverage tables and doc maps across reports | Final proofread pass | Partial
I1.1 | Incident Response | I1 | IR Environment Setup | Wazuh SIEM on Parrot OS (VirtualBox) with agent deployment | Week 3 | Wazuh on Docker (Mac) + Kali agent in UTM (Parrot/VirtualBox not used) | ENVIRONMENT MISMATCH: get instructor sign-off that Kali/UTM substitutes | Partial | 2026-10-12
I1.2 | Incident Response | I1 | IR Environment Setup | Log collection configuration from Parrot OS | Week 3 | Kali agent 002 shipping auth/journald events; Firewall_IDS_IPS report localfile config | None beyond naming Kali instead of Parrot | Done
I1.3 | Incident Response | I1 | IR Environment Setup | Creation of 3 custom alert rules for security events | Week 9 | Custom rules 100002/100003, 100010/100011, 100020/100021 written Oct 5-8 | Capture local_rules.xml + logtest; fix doc rule-ID conflicts | Partial | 2026-10-14
I1.4 | Incident Response | I1 | IR Environment Setup | Wireshark configured with proper capture filters | Testing week | Network_Security_Tools_Report sec. 1 (filter: host 10.11.3.57 and tcp port 22) | That section was drafted - run a real capture and screenshot it | Partial
I1.5 | Incident Response | I1 | IR Environment Setup | Volatility framework with memory analysis configuration | Testing week (stretch) | None | Install Volatility 3 on Kali, document config | Not started | 2026-10-29
I1.6 | Incident Response | I1 | IR Environment Setup | System logging from both Parrot OS and macOS ingested into Wazuh | Week 10 | Kali ingestion works | No macOS agent: enroll the Mac and show events in the dashboard | Partial | 2026-10-19
I2.1 | Incident Response | I2 | Incident Detection and Analysis | Analysis of both Parrot OS and macOS logs in Wazuh with methodology | Week 10 / Testing | Kali analysis complete (Methodology) | Add macOS analysis after I1.6 | Partial | 2026-10-19
I2.2 | Incident Response | I2 | Incident Detection and Analysis | Investigation of 1 suspicious login: host-to-Parrot log correlation, timeline, alert validation | Week 8 | SOC-CASE-2026-0142; note source IP 192.168.64.3 is Kali's own address (self-generated test) | Add host-side (macOS) log correlation to the timeline | Partial | 2026-10-26
I2.3 | Incident Response | I2 | Incident Detection and Analysis | Classification of 3 distinct incidents using the taught severity matrix | Testing week | 1 classified (0142 = High). Candidates ready: 2026-09-30 blocked run, CIS SCA 19005 (score 27%), Windows 4738 events, GIMP CVEs | Write and classify 2 more | Partial | 2026-10-26
I2.4 | Incident Response | I2 | Incident Detection and Analysis | Documented methodologies and potential security implications | Week 7-8 | Threat_Detection_Principles.md; Methodology sec. 5 | None | Done
I3.1 | Incident Response | I3 | Incident Response and Containment | Network isolation: interface configuration, firewall rules, segmentation via VM networking | Week 9 | Firewall_IDS_IPS report (ufw rules); Network_Topology (LAN segmentation) | Demonstrate interface down + UTM network-mode change with screenshots | Partial | 2026-10-12
I3.2 | Incident Response | I3 | Incident Response and Containment | Evidence preservation: file system artifacts, network captures, memory dumps | Testing week | pcap replay via run_ids.sh; alert records quoted verbatim | No file-system artifact collection or memory dump yet | Partial | 2026-10-27
I3.3 | Incident Response | I3 | Incident Response and Containment | Containment playbook: host isolation, traffic blocking, service shutdown | Week 9 - Approval Workflow | Methodology and IR Plan describe containment decisions (source block, isolation declined with reason) | Standalone playbook with commands | Partial | 2026-10-12
I4.1 | Incident Response | I4 | Digital Evidence Management | Live data collection: system state, processes, network connections | Testing week | None | Run and save ps/ss/lsof-style output on Kali | Not started | 2026-10-27
I4.2 | Incident Response | I4 | Digital Evidence Management | Basic memory analysis with Volatility, performed and documented | Testing week (stretch) | None | Capture memory, run Volatility, document | Not started | 2026-10-29
I4.3 | Incident Response | I4 | Digital Evidence Management | Disk acquisition with imaging tools and proper procedures | Testing week (stretch) | None | Image a VM disk, record hash | Not started | 2026-10-29
I4.4 | Incident Response | I4 | Digital Evidence Management | Chain of custody documentation for all collected evidence | Testing week | Template Section D has 'where preserved' and 'integrity' columns | A real custody form with hashes and handoffs | Partial | 2026-10-27
I4.5 | Incident Response | I4 | Digital Evidence Management | Timeline combining macOS and Parrot OS logs with clear analysis | Testing week | Kali-only timeline in 0142 | Add macOS events (depends on I1.6) | Partial | 2026-10-26
I5.1 | Incident Response | I5 | IR Documentation and Reporting | IR playbook: common incidents, tool-specific commands for Parrot OS, evidence steps | Documentation week | Incident_Response_Plan.md; Methodology runbook | Add Kali command-level steps | Partial | 2026-11-02
I5.2 | Incident Response | I5 | IR Documentation and Reporting | Incident tracking system documenting details, actions, timeline | Week 9 - Approval Buttons | TheHive 5.2.16 case #142 with template tasks and audit timeline | None | Done
I5.3 | Incident Response | I5 | IR Documentation and Reporting | Complete incident report for 1 security event in a standard format | Week 8 | IR report Part 3 (SOC-CASE-2026-0142) | None | Done
I5.4 | Incident Response | I5 | IR Documentation and Reporting | Documentation of all IR tools and procedures with usage explanations | Documentation week | SOC_Operations.md tool section | Add Volatility, Wireshark, imaging tool entries | Partial | 2026-11-02
I6.1 | Incident Response | I6 | Post-Incident Procedures | Recovery procedures: VM environment, OS recovery, network configuration | Documentation week | Recovery section of Methodology (no restore needed in 0142) | Document UTM snapshot restore + network config restore | Partial | 2026-11-02
I6.2 | Incident Response | I6 | Post-Incident Procedures | Root cause analysis: timeline, contributing factors, technical findings | Week 8 | IR report sec. 3.9 (weak credential, password SSH enabled, no notification path) | None | Done
I6.3 | Incident Response | I6 | Post-Incident Procedures | Recovery validation checklist with testing procedures | Documentation week | None as a checklist | Write checklist with pass/fail tests | Not started | 2026-11-02
I6.4 | Incident Response | I6 | Post-Incident Procedures | IR process improvement recommendations from lessons learned | Week 8 | Findings I.1-I.9 with owners and dates | None | Done

## Board Additions
Board additions: subitems that fold the rubrics into the existing weeks
Add each row as a Subitem under the named parent on the Monday board (Status blank = not started, same as the existing board). Rubric IDs refer to the 'Rubric Checklist' sheet.
Parent item (existing) | Parent date | New subitem (Name) | Person | Status | Date | Rubric IDs | Deliverable / evidence to produce
Design the Approval Workflow | 2026-10-12 | Confirm with instructor that Kali (UTM) + Dockerized Wazuh on the Mac substitutes for Parrot OS (VirtualBox) | Kyrell Green |  | 2026-10-12 | I1.1 | Written confirmation (email/Slack) saved with the project docs
Design the Approval Workflow | 2026-10-12 | Write the containment playbook for Kali: isolate interface, block IPs, stop services, with an approval tier per action | Kyrell Green |  | 2026-10-12 | I3.3, I3.1 | Playbook .md with exact commands + screenshots of interface down and UTM network-mode change
Implement the Approval Gate | 2026-10-13 | Configure alert routing + notification (Wazuh to TheHive, or email) and capture a test alert arriving | Kyrell Green |  | 2026-10-13 | M1.4 | ossec.conf excerpt + screenshot of the alert landing in TheHive/inbox
Build the Analyst Console (CLI Version) | 2026-10-14 | Capture proof for custom rules 100002-100021: local_rules.xml, logtest output, dashboard hit | Kyrell Green |  | 2026-10-14 | M1.3, M1.5, I1.3 | 3 screenshots per scenario (auth, Windows process/file, network)
Adversarial Testing | 2026-10-15 | Reconcile docs with live config (SIEM_Implementation sec. 2 and 4.1; rule ID 100010 now used differently) | Kyrell Green |  | 2026-10-15 | M1.3, M1.4 | Corrected SIEM_Implementation.md that matches the running manager
Learn Streamlit Fundamentals | 2026-10-19 | Enroll the macOS host as a Wazuh agent and confirm log ingestion | Kyrell Green |  | 2026-10-19 | I1.6, I2.1 | Agents page showing Kali, Windows 007 and macOS Active + a macOS event in Discover
Build the Alert Queue | 2026-10-20 | Write scripts/health_check.py (agent status, indexer cluster health, manager status, disk/RAM) and define alert baselines + thresholds | Kyrell Green |  | 2026-10-20 | M3.3, M3.4 | health_check.py output + baseline table (alerts/day per agent, failed logins per source)
Display Investigation Results | 2026-10-21 | Add a health + metrics panel to the Streamlit dashboard (real-time security status) | Kyrell Green |  | 2026-10-21 | M4.4, M3.4 | Dashboard screenshot
Implement Approval Buttons | 2026-10-22 | Write approve/reject decisions to the TheHive case timeline (incident tracking evidence) | Kyrell Green |  | 2026-10-22 | I5.2 | TheHive case showing the analyst decision with timestamp
Generate the Test Dataset | 2026-10-26 | Re-run Hydra with the macOS agent live; correlate macOS + Kali events into one timeline | Kyrell Green |  | 2026-10-26 | I2.2, I4.5, I2.1 | Combined timeline table + annotated log excerpts
Generate the Test Dataset | 2026-10-26 | Complete 2 more incident cases with Incident_Response_Template (e.g. CVE rule 23504, SCA 19005, Windows event 4738) and classify all 3 with the severity matrix | Kyrell Green |  | 2026-10-26 | M4.1, I2.3 | 2 new case files + a 3-row severity classification table
Run Full System Evaluation | 2026-10-27 | Live data collection on Kali (processes, connections, system state), pcap, file hashes, chain-of-custody form | Kyrell Green |  | 2026-10-27 | I4.1, I3.2, I4.4 | Saved command output, SHA-256 list, signed custody form
Measure Performance | 2026-10-28 | Build the metrics table: operational (detect/declare/contain times), coverage (agents, MITRE techniques), effectiveness (accuracy, FP, FN) | Kyrell Green |  | 2026-10-28 | M4.2 | Metrics table with measurement method per row
Improve the Investigation Engine | 2026-10-29 | STRETCH: memory capture + Volatility analysis; disk image with an imaging tool | Kyrell Green |  | 2026-10-29 | I4.2, I4.3, I1.5, I3.2 | Volatility output + image hash
Write the Technical Documentation | 2026-11-02 | Recovery procedures + validation checklist (UTM snapshot restore, network config restore) | Kyrell Green |  | 2026-11-02 | I6.1, I6.3 | Recovery section + checklist with pass/fail tests
Write the Technical Documentation | 2026-11-02 | Tool-by-tool IR command appendix (Wazuh, TheHive, Wireshark, Volatility) | Kyrell Green |  | 2026-11-02 | I5.1, I5.4 | Appendix with command, purpose, example output
Write Your Portfolio Case Study | 2026-11-04 | Security summary report: alert trends, significant findings, recommendations | Kyrell Green |  | 2026-11-04 | M4.3 | 2-page report using indexer alert counts by day/rule
Final QA & Project Release | 2026-11-05 | Sign-off: every row on Rubric Checklist is Done and has an evidence link | Kyrell Green |  | 2026-11-05 | All | Rubric Summary shows 100%

## updates
Kyrell's Project Board - AI-agentic SOC triage engine | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
12715428090 | Build the SIEM FastAPI Service | Update |  | Kyrell Green | 05/August/2026 04:32:28 PM | Description ----------- Create a second FastAPI application that serves SIEM events. Implement endpoints to retrieve alerts, search historical events, and filter by user, host, or severity. Example endpoints: GET /events GET /events/user/{username} GET /events/host/{hostname} GET /events/severity/{level} Deliverable * Working SIEM API * Database integration * Search functionality | 0 |  | 5435262661
12715429015 | Design the SIEM Event Schema | Update |  | Kyrell Green | 05/August/2026 04:30:32 PM | Description ----------- Study the structure of SIEM events and define your own simplified event format. Include timestamps, hostnames, usernames, event IDs, event types, severity, MITRE ATT&CK references, and descriptions. Populate PostgreSQL with baseline events. Deliverable * SIEM event schema * Event database * Baseline event dataset | 0 |  | 5435254530
12715398467 | Integration Testing & Project Review | Update |  | Kyrell Green | 05/August/2026 04:35:12 PM | Description ----------- Test everything built during the first three weeks. Verify that PostgreSQL stores data correctly, the Identity API returns expected results, and the SIEM API can query historical events. Clean up project folders, remove unused code, update the README, and commit a stable milestone version. Deliverable * Identity API complete * SIEM API complete * PostgreSQL populated * Stable project milestone * Updated documentation | 0 |  | 5435272317
12715481534 | Generate SIEM Attack Events | Update |  | Kyrell Green | 05/August/2026 04:33:35 PM | Description ----------- Extend your synthetic data generator to create realistic security events that correspond to your four attack scenarios. Ensure events appear in chronological order and can later be correlated with identity and endpoint information. Deliverable * Historical SIEM events * Attack-related logs * Correlated event timeline | 0 |  | 5435266490
12715482241 | Design the EDR Data Model | Update |  | Kyrell Green | 05/August/2026 04:38:19 PM | Description ----------- Study what endpoint detection platforms monitor. Design your own simplified endpoint telemetry schema. Each endpoint should have: * Hostname * Username * Operating System * Running Processes * Network Connections * Parent/Child Processes * File Activity * Risk Score Create PostgreSQL tables to store endpoint activity. Deliverables * PostgreSQL EDR tables * Endpoint schema * Initial documentation | 0 |  | 5435289131
12715483928 | Build the EDR FastAPI Service | Update |  | Kyrell Green | 05/August/2026 04:40:43 PM | Description ----------- Create the third FastAPI application. Example endpoints: GET /devices GET /devices/{hostname} GET /devices/{hostname}/processes GET /devices/{hostname}/connections Return PostgreSQL data instead of placeholder JSON. Deliverables * Working EDR API * PostgreSQL integration * API documentation | 0 |  | 5435298816
12715481949 | End-to-End API Integration | Update |  | Kyrell Green | 05/August/2026 04:41:57 PM | Description ----------- Run all three APIs simultaneously. Verify: Identity API ↓ SIEM API ↓ EDR API Confirm each API returns valid JSON. Test every endpoint using Swagger. Fix bugs. Organize folders. Commit milestone. Deliverables Identity API SIEM API EDR API PostgreSQL connected | 0 |  | 5435302737
12715484072 | Generate Synthetic Endpoint Telemetry | Update |  | Kyrell Green | 05/August/2026 04:39:03 PM | Description ----------- Create Python scripts that generate realistic endpoint activity. Examples: * Chrome launches * Outlook launches * PowerShell execution * CMD execution * Network connections * File downloads * USB insertions Inject suspicious behavior for your four attack scenarios. Deliverables * Endpoint dataset * Synthetic telemetry generator * Attack behaviors | 0 |  | 5435292972
12726202658 | Project Setup & Development Environment | Update |  | Kyrell Green | 05/August/2026 04:10:45 PM | Description ----------- Set up the entire development environment from scratch. Create the Git repository, Python virtual environment, install all required packages, and initialize PostgreSQL. Create the project's folder structure (agent, APIs, database, frontend, docs, tests). Verify that PostgreSQL is running and that Python can successfully connect to it. Finish by making the first Git commit. Deliverable * Working virtual environment * PostgreSQL running * Project folder structure * Initial Git repository | 0 |  | 5435152996
12726202658 | Project Setup & Development Environment |  | Reply | Kyrell Green | 10/September/2026 04:54:14 PM | The SIEM pillar is no longer a locally simulated Splunk/FastAPI mock. It is replaced by **the real Wazuh 4.14.7 single-node deployment already running in this project's SOC lab** (Docker, hosted on the development Mac). Wazuh is now **both** the alert source (where detections originate) **and** the historical evidence pillar (SIEM history queries). Alert ingestion switches from a hand-fed Splunk-ES-shaped JSON file to live pulls file to live pulls from the Wazuh API. | 0 |  | 5537043117 | 5435152996
12726300556 | Design the Alert Schema | Update |  | Kyrell Green | 05/August/2026 04:11:39 PM | Description ----------- Study how SOC alerts are structured and design the JSON format your project will accept. Define fields such as alert ID, timestamp, username, hostname, source IP, destination IP, severity, alert type, and description. Create several sample alert JSON files that will be used throughout the project. Deliverable * Final alert JSON schema * Five sample alerts * JSON validation completed | 0 |  | 5435156387
12726350604 | Learn FastAPI Fundamentals | Update |  | Kyrell Green | 05/August/2026 04:17:19 PM | Description ----------- Install FastAPI and Uvicorn. Build your first API application, create GET endpoints, understand decorators, automatic documentation, and JSON responses. Learn how to test endpoints using the built-in Swagger interface. Deliverable * First FastAPI application * Three working endpoints * Swagger documentation accessible | 0 |  | 5435185307
12726389663 | Build the Identity API Skeleton | Update |  | Kyrell Green | 05/August/2026 04:21:31 PM | Description ----------- Create the Identity microservice. Define the API routes you expect the AI agent to use later, such as retrieving a user profile, login history, and MFA status. Use placeholder data for now to verify the API structure. Example endpoints: GET /users/{username} GET /users/{username}/logins GET /users/{username}/mfa Deliverable * Identity API running * Three working endpoints * Placeholder responses | 0 |  | 5435201449
12726389663 | Build the Identity API Skeleton |  | Reply | Kyrell Green | 10/September/2026 04:02:39 PM | Instead of building everything entirely from scratch, Wazuh is being utilized with simple login, note admin privileges are required via a DAE staff member. | 0 | 3239653441 | 5536829367 | 5435201449
12726484445 | Learn Pydantic Models | Update |  | Kyrell Green | 05/August/2026 04:24:57 PM | Description ----------- Learn how FastAPI uses Pydantic for validation. Create models for users, login events, MFA settings, and user privileges. Understand request validation and response models. Deliverable * User model * Login model * MFA model * Validation working | 0 |  | 5435222482
12726437133 | Generate Synthetic Identity Data | Update |  | Kyrell Green | 05/August/2026 04:26:11 PM | Description ----------- Create Python scripts that generate realistic user accounts. Each user should include usernames, departments, managers, privilege levels, login history, MFA settings, and locations. Save this data in PostgreSQL. Deliverable * 50–100 synthetic users * Database populated * Data generation script | 0 |  | 5435226641
12726460552 | Connect FastAPI to PostgreSQL | Update |  | Kyrell Green | 05/August/2026 04:27:10 PM | Description ----------- Replace placeholder responses with live database queries. Learn SQLAlchemy (or another PostgreSQL library you choose) to retrieve user information from PostgreSQL. Verify all Identity API endpoints return real data. Deliverable * Database connection * Live API queries * Identity API fully connected | 0 |  | 5435231027
12726460552 | Connect FastAPI to PostgreSQL |  | Reply | Kyrell Green | 14/September/2026 04:20:37 PM | Not necessarily needed for the minimum value product/project | 0 |  | 5545656198 | 5435231027
12726485623 | Attack Scenario Generator | Update |  | Kyrell Green | 05/August/2026 04:27:57 PM | Description ----------- Write functions that inject realistic attack behaviors into user accounts. Implement four scenarios: * Credential stuffing * Brute-force attack * Phishing compromise * Ransomware precursor Each scenario should modify login history and account activity so the AI agent has something meaningful to investigate later. Deliverable * Four attack generators * Realistic synthetic attack data | 0 |  | 5435235192
12726641813 | Weekly Goal | Update |  | Kyrell Green | 05/August/2026 04:43:31 PM | Finish the last mock service (EDR). By the end of this week you'll have three complete backend services that simulate a real SOC environment. | 0 |  | 5435307848
12726676250 | Learn LangGraph Fundamentals | Update |  | Kyrell Green | 05/August/2026 04:48:36 PM | Description ----------- Install: * LangChain * LangGraph Learn: * Nodes * Edges * State * Tool calling * Workflow execution Create a simple graph that prints: Start ↓ Investigate ↓ Finish Don't connect any APIs yet. Deliverables * First LangGraph workflow * Working StateGraph | 0 |  | 5435325620
12726676250 | Learn LangGraph Fundamentals | Update |  | Abhinav Piratla | 14/September/2026 04:01:51 PM |  | 0 | 3246262773, 3246262800 | 5545568935
12726676250 | Learn LangGraph Fundamentals |  | Reply | Abhinav Piratla | 14/September/2026 04:02:04 PM | @Kyrell Green Let me know if you cannot access it | 1 |  | 5545569842 | 5545568935
12726699225 | Create the Investigation State | Update |  | Kyrell Green | 05/August/2026 04:50:39 PM | Description ----------- Design the information that moves through the graph. Example state: alert identity_context siem_context edr_context timeline report recommendation Create your first TypedDict (or Pydantic model) for graph state. Deliverables * Investigation State * Graph schema | 0 |  | 5435333588
12726690477 | Build the Supervisor Node | Update |  | Kyrell Green | 05/August/2026 04:52:11 PM | Description ----------- Create the AI supervisor. Its only job: Receive an alert ↓ Determine "What information do I need?" For now the supervisor only returns a list. Example: Investigate Identity Investigate SIEM Investigate EDR No tool calling yet. Deliverables * Supervisor node * Investigation planning | 0 |  | 5435339485
12726726941 | Build the First Tool | Update |  | Kyrell Green | 05/August/2026 04:53:39 PM | Description ----------- Connect the Identity API. The supervisor now actually requests identity information. Flow: Alert ↓ Supervisor ↓ Identity API ↓ Receive response ↓ Print result Deliverables * First LangGraph tool * Identity lookup working | 0 |  | 5435344411
12726794813 | Weekly Goal | Update |  | Kyrell Green | 05/August/2026 04:55:26 PM | Introduce AI into the project. This week you're learning LangGraph while keeping the workflow simple. | 0 |  | 5435350399
12726794813 | Weekly Goal |  | Reply | Kyrell Green | 16/September/2026 06:31:01 PM | Implementing course rubric to fit into the project, Security Operations Center1: Prepare SOC Operations Documentation, Document SIEM Implementation, Document Threat Detection Principles, Document Incident Response Methodology. Cybersecurity Basics1: Create an Incident Response Plan, Develop a Comprehensive Security Policy, Apply Encryption Techniques, Demonstrate Legal and Ethical Compliance. | 0 |  | 5553664637 | 5435350399
12726786427 | Connect the SIEM Tool | Update |  | Kyrell Green | 05/August/2026 04:56:20 PM | Description ----------- Create another LangGraph tool. The supervisor should now call the SIEM API. Retrieve: * Historical alerts * Failed logins * User activity * Host activity Deliverables * SIEM tool connected | 0 |  | 5435353545
12726761012 | Connect the EDR Tool | Update |  | Kyrell Green | 05/August/2026 04:59:20 PM | Description ----------- Create the third tool. Retrieve endpoint telemetry. Examples: Running processes Network connections Suspicious activity Now your graph should gather information from: Identity * SIEM * EDR Deliverables * EDR tool * Three tools connected | 0 |  | 5435364790
12726834681 | Build the Investigation Timeline | Update |  | Kyrell Green | 05/August/2026 05:01:12 PM | Description ----------- Take the outputs from all three APIs. Merge them into a chronological timeline. Example: 08:00 Failed Login ↓ 08:05 VPN Login ↓ 08:07 PowerShell launched ↓ 08:10 Outbound Connection Don't worry about AI summaries yet. Focus only on chronology. Deliverables * Timeline builder * Unified investigation object | 0 |  | 5435372960
12726816232 | Complete the First Automated Investigation | Update |  | Kyrell Green | 05/August/2026 05:10:39 PM | Description ----------- Run a complete alert. Example: Alert arrives ↓ Supervisor analyzes alert ↓ Calls Identity API ↓ Calls SIEM API ↓ Calls EDR API ↓ Creates timeline ↓ Print investigation This is the first time your project behaves like an investigation engine. Debug everything. Refactor messy code. Commit. Deliverables Three APIs connected LangGraph Supervisor Tool calling Automated investigation | 0 |  | 5435414995
12726841316 | Weekly Goal | Update |  | Kyrell Green | 05/August/2026 05:03:37 PM | Turn the workflow into an actual investigation. | 0 |  | 5435382769
12727548441 | Weekly Summary | Update |  | Kyrell Green | 05/August/2026 05:59:51 PM | Transform raw evidence into a coherent security investigation by correlating data from all three sources and mapping it to MITRE ATT&CK techniques. | 0 |  | 5435667996
12727557582 | Design the Investigation Correlation Engine | Update |  | Kyrell Green | 05/August/2026 06:00:48 PM | Description ----------- Right now, your Identity API, SIEM API, and EDR API each return separate pieces of information. Your goal today is to design a single Python object that combines them into one investigation. Create a unified structure that contains: * Original alert * Identity findings * SIEM findings * EDR findings * Timeline events * Risk indicators Think of this as the "case file" that every later step will use. Deliverables * Investigation data model * Unified case object * Documentation of investigation flow | 0 |  | 5435672399
12727525999 | Build the Correlation Engine | Update |  | Kyrell Green | 05/August/2026 06:01:59 PM | Description ----------- Write Python logic that merges findings from the three APIs. Example: Alert: Impossible Travel ↓ Identity: 12 failed logins ↓ SIEM: VPN login from Germany ↓ EDR: PowerShell executed ↓ One Investigation Your goal is not AI reasoning yet—just combining related evidence. Deliverables * Correlation function * Merged investigation * Single investigation object | 0 |  | 5435680040
12727577701 | Implement MITRE ATT&CK Mapping | Update |  | Kyrell Green | 05/August/2026 06:03:40 PM | Description ----------- Create a simple rule-based mapping system. For example: Credential Stuffing ↓ Credential Access ↓ T1110 Another example: PowerShell ↓ Execution ↓ T1059 Start with only the techniques needed for your four attack scenarios. Do not try to implement the entire ATT&CK framework. Deliverables * ATT&CK lookup table * Rule-based mapper * Technique tags | 0 |  | 5435685997
12727597585 | Validate All Attack Scenarios | Update |  | Kyrell Green | 05/August/2026 06:04:44 PM | Description ----------- Run all four attack scenarios. Verify: * Timeline is correct * Correlation works * ATT&CK mapping is accurate * No duplicate events appear Fix any inconsistencies. Commit milestone. Deliverables Four scenarios working ATT&CK mapped Correlation complete | 0 |  | 5435689801
12727636140 | Weekly Goal | Update |  | Kyrell Green | 05/August/2026 06:07:00 PM | Teach the AI to explain investigations the way a SOC analyst would write them. | 0 |  | 5435698781
12727631792 | Design the Investigation Report | Update |  | Kyrell Green | 05/August/2026 06:09:33 PM | Description ----------- Before involving the LLM, define the report structure. Suggested sections: Alert Summary Investigation Timeline Identity Findings SIEM Findings Endpoint Findings MITRE ATT&CK Think about what information a Tier 1 analyst needs at a glance. Deliverables * Report template * Report data model | 0 |  | 5435709713
12727694453 | Generate AI Investigation Summaries | Update |  | Kyrell Green | 05/August/2026 06:11:42 PM | Description ----------- Connect the investigation object to your LLM. The model should generate: * Executive summary * What happened * Why it's suspicious * Recommended next steps Keep prompts focused and structured. Deliverables * AI-generated summary * Prompt template * Structured output | 0 |  | 5435717523
12727666620 | Implement Investigation Logging | Update |  | Kyrell Green | 05/August/2026 06:12:59 PM | Description ----------- Every decision the agent makes should be recorded. Log things like: Identity lookup requested ↓ Found 12 failed logins ↓ Queried SIEM ↓ Detected impossible travel ↓ Queried EDR ↓ Found PowerShell execution Store these logs in PostgreSQL so they can be reviewed later. Deliverables * Investigation log table * Decision logging * PostgreSQL integration | 0 |  | 5435721940
12727688142 | Complete the First End-to-End Investigation | Update |  | Kyrell Green | 05/August/2026 06:14:55 PM | Description ----------- Run the complete workflow. Alert ↓ Supervisor ↓ Identity ↓ SIEM ↓ EDR ↓ Correlation ↓ ATT&CK ↓ AI Report ↓ Logs This is your first complete investigation pipeline. Fix bugs. Refactor code. Commit. Deliverables Complete investigation workflow AI-generated report Investigation logs | 0 |  | 5435729662
12727747896 | Weekly Goal | Update |  | Kyrell Green | 05/August/2026 06:16:15 PM | Finish the SOC analyst experience by ensuring the AI can recommend—but never execute—containment actions. | 0 |  | 5435735931
12727706291 | Design the Approval Workflow | Update |  | Kyrell Green | 05/August/2026 06:17:28 PM | Description ----------- Decide which actions require analyst approval. Examples: * Disable user account * Isolate endpoint * Escalate incident * Close investigation Create a simple approval state. Possible values: Pending Approved Rejected Deliverables * Approval model * Workflow diagram | 0 |  | 5435741690
12727753589 | Implement the Approval Gate | Update |  | Kyrell Green | 05/August/2026 06:19:07 PM | Description ----------- Modify your LangGraph workflow. Instead of ending after the report, it should pause. New flow: Report Generated ↓ Recommendation ↓ Wait For Analyst ↓ Approved or Rejected No action should continue until a decision is made. Deliverables * Approval node * LangGraph pause * Resume workflow | 0 |  | 5435749464
12727762641 | Build the Analyst Console (CLI Version) | Update |  | Kyrell Green | 05/August/2026 06:20:43 PM | Description ----------- Before building the dashboard, create a simple command-line interface. The analyst should be able to: * View report * View timeline * View ATT&CK techniques * Approve * Reject Keep it simple. Deliverables * CLI interface * Approval interaction | 0 |  | 5435755457
12727768361 | Adversarial Testing | Update |  | Kyrell Green | 05/August/2026 06:22:01 PM | Description ----------- Attempt to "break" your workflow. Test questions like: * Can the AI skip approval? * What if the recommendation is empty? * What if PostgreSQL is unavailable? * What if an API returns no data? * What if the alert is malformed? Document failures and fix them. Commit milestone. Deliverables Approval gate CLI analyst interface Security testing | 0 |  | 5435761375
12727892990 | Weekly Goal | Update |  | Kyrell Green | 05/August/2026 06:25:23 PM | Replace the command-line interface with a simple SOC analyst dashboard using Streamlit. By the end of this week, you'll have something that looks like a real SOC application. | 0 |  | 5435774459
12727820750 | Learn Streamlit Fundamentals | Update |  | Kyrell Green | 05/August/2026 06:27:02 PM | Description ----------- Install Streamlit and build your first application. Learn how to create: * Headers * Buttons * Sidebars * Tables * JSON viewers * Session state Don't connect anything yet. Focus only on understanding Streamlit. Example layout: AI SOC Dashboard Alert Queue Investigation Report Timeline Approve / Reject Deliverables * Streamlit installed * First dashboard * Basic layout completed | 0 |  | 5435781909
12727818972 | Build the Alert Queue | Update |  | Kyrell Green | 05/August/2026 06:27:55 PM | Description ----------- Display alerts stored in PostgreSQL. Each alert should show: * Alert ID * Severity * User * Host * Status * Time Allow the analyst to select an alert. When selected: Run Investigation Deliverables * Alert table * Alert selection * PostgreSQL integration | 0 |  | 5435785484
12727878257 | Display Investigation Results | Update |  | Kyrell Green | 05/August/2026 06:28:47 PM | Description ----------- Connect your investigation engine. Once an investigation completes, display: * Alert Summary * Timeline * Identity Findings * SIEM Findings * Endpoint Findings * MITRE ATT&CK * AI Summary Everything should now be visible inside Streamlit. Deliverables * Investigation viewer * Timeline display * Report display | 0 |  | 5435788481
12727914405 | Implement Approval Buttons | Update |  | Kyrell Green | 05/August/2026 06:32:09 PM | Description ----------- Replace the CLI approval. Create two buttons. Approve Reject Store analyst decisions in PostgreSQL. Display investigation status. Example: Pending ↓ Approved ↓ Closed Deliverables ✅ Complete dashboard ✅ Investigation viewer ✅ Approval buttons | 0 |  | 5435800761
12727911635 | Weekly Goal | Update |  | Kyrell Green | 05/August/2026 06:34:16 PM | Treat your project like a real security product. Measure how well it performs. | 0 |  | 5435809676
12727960162 | Generate the Test Dataset | Update |  | Kyrell Green | 05/August/2026 06:35:05 PM | Description ----------- Create a large collection of alerts. Suggested distribution: * 10 Credential Stuffing * 10 Brute Force * 10 Phishing * 10 Ransomware Precursors * 10 Benign Alerts Store labels in PostgreSQL. This becomes your "ground truth." Deliverables * 50 labeled alerts * Test dataset | 0 |  | 5435812427
12727943787 | Run Full System Evaluation | Update |  | Kyrell Green | 05/August/2026 06:36:22 PM | Description ----------- Run every alert through your investigation engine. Record: * Investigation completed? * Correct ATT&CK? * Correct recommendation? * Processing time Save results. Deliverables * Evaluation results * Processing times | 0 |  | 5435817488
12727971285 | Measure Performance | Update |  | Kyrell Green | 05/August/2026 06:37:46 PM | Description ----------- Calculate: * Detection Accuracy * False Positives * False Negatives * Average Investigation Time * Average Report Generation Time Create a simple evaluation summary. Example: Accuracy 92% Average Investigation 7.4 seconds False Positives 3 False Negatives 2 (These numbers are examples—you'll use whatever your actual results are.) Deliverables * Evaluation report * Metrics summary | 0 |  | 5435822521
12727989038 | Improve the Investigation Engine | Update |  | Kyrell Green | 05/August/2026 06:39:37 PM | Description ----------- Review failures. Ask: Why did the AI make this decision? Can prompts improve? Can rules improve? Can correlation improve? Spend today improving quality rather than adding features. Commit. Deliverables Better prompts Better correlation Improved accuracy | 0 |  | 5435829424
12728068589 | Weekly Goal | Update |  | Kyrell Green | 05/August/2026 06:43:11 PM | Transform your project from "finished" into something you're proud to demonstrate in interviews. | 0 |  | 5435843556
12727982226 | Write the Technical Documentation | Update |  | Kyrell Green | 05/August/2026 06:44:18 PM | Description ----------- Create: * README * Installation Guide * Project Overview * Folder Structure * Architecture Diagram * API Documentation * Database Schema * How to Run Think of this as documentation for another developer joining your project. Deliverables * Complete README * Technical documentation | 0 |  | 5435847468
12728018274 | Record the Project Demo | Update |  | Kyrell Green | 05/August/2026 06:45:36 PM | Description ----------- Record a 5–10 minute walkthrough. Suggested flow: Receive Alert ↓ Run Investigation ↓ Timeline Created ↓ ATT&CK Mapping ↓ AI Report ↓ Approve ↓ Close Alert Explain what the AI is doing at each stage. Deliverables * Demo video * Demo script | 0 |  | 5435852490
12728091315 | Write Your Portfolio Case Study | Update |  | Kyrell Green | 05/August/2026 06:46:18 PM | Description ----------- Write a case study that answers: * What problem does this solve? * Why did you build it? * Architecture * Technologies used * Challenges encountered * Lessons learned * Results (using your measured metrics) Include screenshots from your dashboard. Deliverables * Portfolio article * Project screenshots | 0 |  | 5435855133
12728038632 | Final QA & Project Release | Update |  | Kyrell Green | 05/August/2026 06:47:19 PM | Description ----------- Perform one last review. Verify: * PostgreSQL works * APIs run correctly * Dashboard works * LangGraph functions correctly * Documentation is complete * GitHub repository is clean Tag the repository as Version 1.0. Celebrate—you've finished the project. Deliverables Version 1.0 GitHub repository Documentation Dashboard Demo Portfolio case study | 0 |  | 5435858629
12737980224 | TEST/Debug | Update |  | Kyrell Green | 02/September/2026 06:27:40 PM | The Wazuh setup with Docker was complete with a UTM VM, indexer, manager, server and dashboard. The only thing left was to deploy an agent, which is where I left off last Thursday, and this was evident when loading the program. However it appears the manager container is crash looping. | 0 | 3222314316 | 5514723528
12737960971 | TEST/Debug | Update |  | Kyrell Green | 02/September/2026 04:49:38 PM | An issue I came across multiple times was limited RAM on the host machines used while off campus, VM's used were an apple silicon laptop with UTM while in class. My Laptop Tablet with 3.98 GB of available RAM, even running a headless ubuntu 22.04 could not handle the docker containers necessary for the installation of Wazuh. I tried to install this on an old beater laptop with linux mint 19-22 and RAM was still a contributing factor... To circumvent this I asked Claude If it was possible to add external storage. Below is the full exchange of information. Good instinct on the storage side — but it's worth separating the two problems, because an SD card only helps one of them. --------------------------------------------- What an SD card via USB-C can fix: disk space --------------------------------------------- Yes, this works for the earlier VERR_DISK_FULL error. You could: * Plug in a USB-C SD card reader with a decent-sized card (64GB+ ideally) * Either move the VM's whole virtual disk (.vdi/.vhd file) onto it, or create a new virtual disk located on the SD card and attach it to the VM * This gives Wazuh's containers/volumes room to actually write data without hitting disk-full errors Caveat: SD cards are typically much slower than an internal SSD/HDD (especially for random I/O, which is exactly what a database like the Wazuh indexer does constantly). It'll work, but expect it to feel sluggish — a Java/OpenSearch data store hammering a slow SD card is not a great pairing. USB 3.x + a fast UHS-II card mitigates this somewhat; a basic USB 2.0 reader with a slow card would be rough. ------------------------------- What an SD card cannot fix: RAM ------------------------------- This is the more important point — the 3.9GB physical RAM ceiling and the disk space problem are unrelated. An SD card adds storage capacity, not memory. The indexer got OOM-killed because there wasn't enough RAM, not because it ran out of disk at that moment (that was a separate, earlier error). Even with unlimited disk space via SD card, the indexer will still fight for memory and likely get killed again once you're under real load. ----------- Bottom line ----------- An SD card is a legitimate fix for the storage half of this, and worth doing regardless. But it won't unblock you on its own — you'd still be stuck on the RAM ceiling for getting the indexer stable. If you want to keep going with local VirtualBox, you'd need both: SD card for storage, and either physical RAM upgrade or drastically closing everything else on the host to squeeze out more MB for the VM. Given the RAM constraint is the harder blocker, is upgrading physical RAM on this machine on the table, or would you rather look at the cloud VM route to sidestep the hardware limits entirely? With that confirmed I have 2 options, use my p/c or the apple silicon based laptop of which both devices are restricted to designated areas. | 0 | 3221995106 | 5514273666
12856971058 | Status Update | Update |  | Kyrell Green | 24/August/2026 03:34:11 PM | This week I familiarized myself with setting up a Virtual Machine specifically Oracle, running ubuntu-24.04.4, and Wuzah a free open-source security platform that unifies security information and enviroment management and extended detection and response. | 0 |  | 5486273821
13076056100 | Status update | Update |  | Elumedon Iweriebor | 18/September/2026 01:23:45 AM | Hi @Kyrell Green Important reminder: please add the status update line item to your board, we won't be adding it for you, so it's on you to keep it current | 0 |  | 5558306801