## kyrell's project board - ai-age
Kyrell's Project Board - AI-agentic SOC triage engine
Week 1- Project Foundation & Planning
Name | Subitems | Person | Status | Date | Checkbox
Project Setup & Development Environment |  | Kyrell Green |  | 2026-08-17
Design the Alert Schema |  | Kyrell Green |  | 2026-08-18
Learn FastAPI Fundamentals |  |  |  | 2026-08-19
Build the Identity API Skeleton |  |  |  | 2026-08-20
|  |  |  | 2026-08-17 to 2026-08-20 | 0/4
Week 2- Building the identity source
Name | Subitems | Person | Status | Date | Checkbox
Learn Pydantic Models |  |  |  | 2026-08-24
Generate Synthetic Identity Data |  |  |  | 2026-08-25
Connect FastAPI to PostgreSQL |  |  |  | 2026-08-26
Attack Scenario Generator |  |  |  | 2026-08-27
|  |  |  | 2026-08-24 to 2026-08-27 | 0/4
Week 3- SIEM mock service
Name | Subitems | Person | Status | Date | Checkbox
Design the SIEM Event Schema |  | Kyrell Green |  | 2026-08-31
Build the SIEM FastAPI Service |  | Kyrell Green |  | 2026-09-01
Generate SIEM Attack Events |  | Kyrell Green |  | 2026-09-02
Integration Testing & Project Review |  | Kyrell Green |  | 2026-09-03
|  |  |  | 2026-08-31 to 2026-09-03 | 0/4
Week 4- Build the EDR Mock Service
Name | Subitems | Person | Status | Date | Checkbox
Design the EDR Data Model |  | Kyrell Green |  | 2026-09-07
Generate Synthetic Endpoint Telemetry |  | Kyrell Green |  | 2026-09-08
Build the EDR FastAPI Service |  | Kyrell Green |  | 2026-09-09
End-to-End API Integration |  | Kyrell Green |  | 2026-09-10
Weekly Goal
|  |  |  | 2026-09-07 to 2026-09-10 | 0/5
WEEK 5- Learn LangGraph & Build the Supervisor
Name | Subitems | Person | Status | Date | Checkbox
Learn LangGraph Fundamentals |  |  |  | 2026-09-14
Create the Investigation State |  |  |  | 2026-09-15
Build the Supervisor Node |  |  |  | 2026-09-16
Build the First Tool |  |  |  | 2026-09-17
Weekly Goal
|  |  |  | 2026-09-14 to 2026-09-17 | 0/5
WEEK 6- Connect the Investigation Engine
Name | Subitems | Person | Status | Date | Checkbox
Connect the SIEM Tool |  |  |  | 2026-09-21
Connect the EDR Tool |  |  |  | 2026-09-22
Build the Investigation Timeline |  |  |  | 2026-09-23
Complete the First Automated Investigation |  |  |  | 2026-09-24
Weekly Goal
|  |  |  | 2026-09-21 to 2026-09-24 | 0/5
WEEK 7- Correlation & MITRE ATT&CK Mapping
Name | Subitems | Person | Status | Date | Checkbox
Design the Investigation Correlation Engine |  |  |  | 2026-09-28
Build the Correlation Engine |  |  |  | 2026-09-29
Implement MITRE ATT&CK Mapping |  |  |  | 2026-09-30
Validate All Attack Scenarios |  |  |  | 2026-10-01
Weekly Goal
|  |  |  | 2026-09-28 to 2026-10-01 | 0/5
WEEK 8- A.I. report Generation
Name | Subitems | Person | Status | Date | Checkbox
Design the Investigation Report |  |  |  | 2026-10-05
Generate AI Investigation Summaries |  |  |  | 2026-10-06
Implement Investigation Logging |  |  |  | 2026-10-07
Complete the First End-to-End Investigation |  |  |  | 2026-10-08
Weekly Goal
|  |  |  | 2026-10-05 to 2026-10-08 | 0/5
WEEK 9- Human-in-the-Loop Workflow
Name | Subitems | Person | Status | Date | Checkbox
Design the Approval Workflow |  |  |  | 2026-10-12
Implement the Approval Gate |  |  |  | 2026-10-13
Build the Analyst Console (CLI Version) |  |  |  | 2026-10-14
Adversarial Testing |  |  |  | 2026-10-15
Weekly Goal
|  |  |  | 2026-10-12 to 2026-10-15 | 0/5
WEEK 10- Build the SOC Dashboard
Name | Subitems | Person | Status | Date | Checkbox
Learn Streamlit Fundamentals |  |  |  | 2026-10-19
Build the Alert Queue |  |  |  | 2026-10-20
Display Investigation Results |  |  |  | 2026-10-21
Implement Approval Buttons |  |  |  | 2026-10-22
Weekly Goal
|  |  |  | 2026-10-19 to 2026-10-22 | 0/5
Testing & Evaluation
Name | Subitems | Person | Status | Date | Checkbox
Generate the Test Dataset |  |  |  | 2026-10-26
Run Full System Evaluation |  |  |  | 2026-10-27
Measure Performance |  |  |  | 2026-10-28
Improve the Investigation Engine |  |  |  | 2026-10-29
Weekly Goal
|  |  |  | 2026-10-26 to 2026-10-29 | 0/5
Documentation, Portfolio & Final Touches
Name | Subitems | Person | Status | Date | Checkbox
Write the Technical Documentation |  |  |  | 2026-11-02
Record the Project Demo |  |  |  | 2026-11-03
Write Your Portfolio Case Study |  |  |  | 2026-11-04
Final QA & Project Release |  |  |  | 2026-11-05
Weekly Goal
|  |  |  | 2026-11-02 to 2026-11-05 | 0/5